## Blad1
		week 1	week 2	week 3	week 4	week 5	week 6	week 7	week 8		week 9	week 10	week 11	week 12		week 13
Matlab simulations				FB moment						Midterm					Deadline	Final Presentation
Incoherent detection w/ hardcoded f										Presentation					Report
Clock Recovery										Presentation					Report
Carrier Recovery
Convolutional codes
OTA design															Design
OTA layout
ADC
Integration
		12-Feb	19-Feb	26-Feb	4-Mar	11-Mar	18-Mar	25-Mar	1-Apr	3-Apr	22-Apr	29-Apr	6-May	13-May	17-May	20-May